## Slide 1: Annex C (Guide): Summary Outputs: Strategic Operational Plan
The following summary slides are derived from Zimbabwe’s National Condom strategic planning process. They present interventions addressing strategic constraints and priorities, and supporting outputs. Slides have been edited.

## Slide 2: Strategic Priority #1
Insufficient planning, coordination, integration and targeting of public sector condom distribution
Oversupply and untargeted distribution is leading to wastage
Lack of targeting of free – including distribution beyond health facilities (“post-facility”)
Insufficient planning and oversight of post-facility distribution
Insufficient integration into SRH, other prevention, treatment
Free distribution beyond health facilities carried out according to TMA plan that targets specific populations mapped in their communities
Improve targeting of public sector condom distribution within context of TMA
  Develop guidance / SoPs on targeting of public sector condoms by post-facility outlet type, cadre, population (within context of TMA & CSM, commercial)
  Mapping in communities to identify targeted distribution in each community, segmentation, priority outlets and plan and
Monitoring system that includes post-facility distribution in place and used to make programme-improvement decisions
Health workers and community service providers confidently and correctly use the ordering system to reduce stock-outs
  Review existing data collection systems that monitor distribution beyond facility; ensure they meet programmatic needs, standardize across facilities and cadres
  Pilot adjusted reporting system
  Analyze & disseminate data, adjust programs as appropriate
  quantify use based on populations in context of TMA
  Develop data collection tool for target populations
  Training on supply chain & provider role in ZAPS, address provider incentives to perform desired role
  Conduct Training for Community health provider cadres on the post-facility tracking system
Strategic Priority
Outputs
Activities that lead to the desired outputs
Constraints addressed
by the Strategic Priority
Adapted from PSI’s “Keystone” process as applied in Zimbabwe

## Slide 3: Strategic Priority #2
Inadequate demand creation, and insufficient segmentation of programs targeting prioritized populations
Youth, AGYW & young men, and KP (not adequately supported by peer education and other media)
Rural (poor coverage & reach)
Lack of standardized messaging & approach for each population (i.e., standard operating procedures)
Population-specific, evidence-based demand creation strategies in place and used to increase reach and coverage of AGYW, young men, and KP
Increase demand creation interventions with sufficient audience segmentation for AGYW, young men and KPs
  Create audience profiles for each of the priority populations
  Develop target audience specific messages for the priority populations
  Develop interventions to deliver the messages for both urban and rural populations
  Implement demand creation initiatives
  Monitor demand creation initiatives
Community service providers’ (all cadres) follow standard operating procedures and tool kits for targeted demand creation for priority pops and targeted distribution
  Develop SOPs & supporting integrated training curriculum for community demand creation cadres for each priority population
  Develop toolkit to standardize the community demand creation efforts specific to target groups
  Create database of the community demand creation workers, identify ToTs for each district
  Training of ToTs on condoms SOP including targeted condom distribution
  Local trainings of community demand creation cadres in all districts
  Monitoring of quality of message delivery by the community demand creation cadres
Strategic Priority
Outputs
Activities that lead to the desired outputs
Constraints addressed
by the Strategic Priority
Adapted from PSI’s “Keystone” process as applied in Zimbabwe

## Slide 4: Strategic Priority #3
Regulatory issues Inhibit commercial actors from reaching potential
High testing fees and numbers of condoms sampled creates a challenges and increases costs
Unlevel playing field for commercial sector: tariffs increase cost to play in market for commercial actors
Delayed registration of products
Duty and VAT regulations in the procurement of condoms revised to support the TMA approach
Address regulatory impediments to commercial sector to create a level playing field
  Advocacy to access foreign currency by private sector players from the RBZ through the engagement with MOHCC
  Mobilization of commercial sector membership to speak with one voice
  The commercial sector to provide data on product distribution to MOHCC (Ministry to aggregate data so as to ensure confidentiality)
Commercial sector actively participates in regulatory policy formulation and feedback
Strategic Priority
Outputs
Activities that lead to the desired outputs
Constraints addressed
by the Strategic Priority
Adapted from PSI’s “Keystone” process as applied in Zimbabwe

## Slide 5: Strategic Priority #4
Limited data and market analytics evidence for program design and monitoring: A lack of…
Data that speaks to the market – distribution, sector contribution, access, etc.
Usage data
Access data – particularly public sector
Market segmentation –consumer preferences
Lack of M&E to show impact of interventions
Insufficient indicators / evaluation framework (including TMA indicators)
Integrated M&E framework completed, disseminated, and followed
Strengthen market analytics and evidence to inform program design and improve monitoring for course corrections
Review the current existing M&E systems
Draft a comprehensive M&E framework addressing existing gaps and incorporate TMA
Convene a stakeholders meeting for input on the draft M&E framework
Finalize the M&E framework
Learning agenda that defines key questions and is used for adaptive management of TMA programming is completed, disseminated, and followed
Operations Research on user preferences, consumer profiling, and condom access completed, disseminated, and used to make programme-improvement decisions
  Convene evidence / M&E working group to confirm specific research priorities for TMA agenda, studies to move forward, and funding to support
  Develop final learning agenda schedule/document
  Conduct a user preference and consumer profiling study amongst prioritized populations
  Conduct a Measuring Access and Performance (MAP) study (private & public sector)
Strategic Priority
Outputs
Activities that lead to the desired outputs
Constraints addressed
by the Strategic Priority
Adapted from PSI’s “Keystone” process as applied in Zimbabwe

## Slide 6: Strategic Priority #5
Stewardship challenges
are hindering the response and limiting alignment of stakeholders
Insufficient Level of Effort & resources at government level
Lack of appreciation, understanding & planning for TMA by key stakeholders
Insufficient coordination – at provincial, district levels
Need to put in place the Condom Strategic Operational Plan – identify milestones, clarify roles and responsibilities, ID funding gaps, synch with TMA
1. Domestic supports procurement of condoms & other programming thru NAC, AIDS Levy, NATF, Health Levy and the fiscus
Increased ownership & stewardship of government for national condom programme, addressing funding, coordination, implementation and M&E in the context of TMA
2. Coordination mechanisms active and valued by stakeholders
3. Level financial playing field for commercial sector
4. Policies that create more favorable environment for condoms in place
Engage the Permanent Secretary to approach relevant funding sources (NAC, MOHCC, MOF)
Prepare concept note on the changing condom landscape, funding gaps and TMA
Follow up meetings with PS on progress regarding funding
Identify policies that require changing (ie School Health Policy & school-based condom interventions & policies impacting KP) & align TMA strategy
Compile data to inform the need for policy realignment
Identify relevant stakeholders and platforms for engagement
Review school health policy and identify opportunities for collaboration/leverage
Advocate for removal Duty & VAT– ensure condoms as Essential Medicines/commodities for commercial sector
  Advocate for consistent application of essential medicines/commodities list to ensure commercial sector does not pay duty/VAT for condoms
  Clarify organogram, TOR, and identify members to constitute the team at provincial and district level
  Support meetings for the team
  Allocate budget to support coordination activities at provincial and district levels
Strategic Priority
Outputs
Activities that lead to the desired outputs
Constraints addressed
by the Strategic Priority
Adapted from PSI’s “Keystone” process as applied in Zimbabwe