## Slide 1
Condom Program Stewardship Strategic Initiative
Core Mgt team Meeting
May 04, 2022

## Slide 2: Today’s Objectives
Alignment on where we’re going – creating a shared vision of success
Understanding of how we’ll get there-
      Leadership and Management Structure
      People and Roles
Identification of Challenges & adjustments
Setting up the week ahead for success

## Slide 3: Today’s Agenda
Topic | Input | Process | Output
Introductions |  | In the chat! Welcome Dr. Namwinga Chintu | 
Alignment on where we are going | Overview of project, Energy, aspirational ideas | Susie & Clemens run us thru the big picture ~ 15 min Participatory Visioning Exercise ~30 min (chris) Revisiting Milestones ~10min (Clemens) | Understanding of why the SI is catalytic Shared themes (with elements of shared vision)
II. Project Architecture & Roles | Ppt overview | Brian & Ana presentation 10 min | Shared understanding of structure
III. Reality check – how it is going and project management adjustments | Energy & positive ideas! | Break into two groups – regional (Global, facilitated by Brian) and country specific (by chris) to identify challenges and opportunities ~ 30 min in break out ~ 30 min in plenary | Shared understanding of challenges and what is causing them, and identified solutions
IV. Deep Dive - Project management | Facilitated discussion | Introduction to RACI matrix, initial pass at roles & responsibilities ~15 min Meeting cadence & structure ~15 min | Understanding RACI matrix is in the works Alignment to the who/what/when of meetings
V. The Week Ahead | Facilitated discussion | Overview of high-level agenda (Brian) 20 min Participants (Ana) Identified tone, tenor, and messaging to support the week ahead (Brian) | Alignment on messaging and roles to set the week up for success

## Slide 4
I. Alignment of where we are going

## Slide 5: Condom Program Stewardship Strategic Initiative
The overall objective of the Condom Program Stewardship SI is to:
Catalyze improvements in the quality of condom programs (more differentiated, equitable, people-centered), which will lead to sustained increases in condom use amongst priority populations, and reduced # of HIV infections (as well as other SRH benefits)
Sub objectives:
Strengthen national and sub-national institutions (NAC, MOH) and systems for improved condom program stewardship
Increase innovation in demand creation and last-mile distribution, including through public-private partnerships
Objectives
Condom use is low in eastern and southern Africa and well below the 90% target
Low capacity in condom program stewardship results in:
  Inefficient priority setting and resource allocation at country level
  Insufficient demand for condoms
  Poor or inconsistent access to condoms for priority populations
  Limited innovation in demand creation and last-mile distribution
  Limited involvement of community actors
Rationale
GF Focal Point: Susie McLean
Total Budget: $5 million
$4.3 million via UNAIDS
New or Continuing SI: New
Under SO-1 (Maximize impact against HIV, TB & malaria), improvements in program stewardship contribute to KPI-5 (Service coverage for key populations) and KPI-8 (Gender and age equality) by increasing condom use, which will reduce the number of new HIV infections.
Under SO-2 (Build resilient and sustainable systems for health) this SI will build the capacity of NACs and other national stakeholders, contributing to KPI-6 (Increase the share of countries with resilient and sustainable national systems for health)
Link to Strategic KPIs & Programmatic Priorities
Malawi, Mozambique, Uganda, Zambia
(All are also receiving Matching Funds)
Focus Countries

## Slide 6: GF Country Grant and the SI
National HIV programme
GF grant
National condom programme
Condom SI
Condom Strategic Initiative
USD 555k package of Catalytic TA
Country focal point/ manager
Country driven TA
Implement public private innovation fund
Condom programming that is more differentiated, effective, equitable, people-centered
TA
GF support on condoms incl. USD 2.5m matching funds

## Slide 7
Condom SI staff at global, regional and country levels
Provision of technical support
Partnerships w/ private sector to facilitate technical support
Coordination with other GF SIs, TSM, SSLN
Technical briefs, guidance & tools
Cross-country coordination forums
Activities
Facilitate self-assessments of country TA priorities to inform TA plan & track stewardship changes
Build a network of TA providers capable of propelling improvements in condom program quality & innovation
Identify and build partnerships with private sector as well as TSM & SSLN to facilitate targeted and coordinated support
Provide continuous, responsive, high-quality & innovative technical support through combination of channels
Develop tools & guidelines to facilitate stewardship, last mile distribution & demand creation capacity building
Assess client satisfaction with TA & use feedback to refine TA model
Analyze, document and disseminate TA model learnings
Outputs
Condom program analytics applied consistently across condom ecosystem
Free condom distribution targets priority populations & coordinated with other market actors (commercial, social marketing)
Demand generation focuses on addressing behavioral drivers in priority populations and uses best practice channels and techniques
Stakeholder satisfaction survey identifies areas where innovative TA model is adding value
Strategic Initiative Outcomes
Improved capacity to steward condom programs
Improved capacity to plan, implement & assess effective & efficient condom procurement and distribution consistent with total market approach best practices
Improved capacity to plan, implement & assess dif-ferentiated demand creation for priority populations
Inputs
Theory of Change
Pathway to country impact
Condom Program Outcome
Increased condom use, equity & sustainability
Intermediate
Programmatic
Increase in condom availability for priority populations in informal locations (i.e., beyond health facilities)
Increased exposure of priority populations to quality demand creation
Condom Program Intermediate Outcome
Improvements in condom access & behavioral de-terminants of use
Increased public-private partnerships for demand creation and last-mile distribution
Improved program stewardship positively influences demand and supply functions
Condom Program Impact
Reduced HIV & STI incidence
Country Grants
SI accountable up to Programmatic Outcomes, which support Country Grants to achieve overall Condom Program Outcomes & Impact

## Slide 8: Milestones to reach by June and December 2022
Indicator | Baseline (if applicable/ available) | Indicator type (process, output, outcome, impact) | Targets |  |  | 
 |  |  | Year 1 (2021) |  | Year 2 (2022) | 
 |  |  | Sem 1 | Sem 2 | Sem 3 | Sem 4
1. Number of countries with an established system that a) collect data on the number of people reached and/or coverage of demand creation programs and b) present analysis in the form of a dashboard to inform decisions by relevant government departments and implementors. | 0 | Outcome |  |  |  | 1 (Malawi and Uganda)
2. Number of countries collecting and reporting on condom distribution and/or availability beyond HF | 0 | Outcome |  |  |  | 1 (Malawi and Uganda)
3. Improvement in NAC/MOH capacity to steward condom programs as measured by % change in annual facilitated self-assessment scores in priority countries | TBD | Outcome |  |  |  | 20% increase from baseline
4. Number of countries with up-to-date formal plans to target free condom distribution outside health facilities within a Total Market Approach (within national program documentation). | 0 | Output | 0 | 1 | 2 (Malawi and Uganda) | 4
5. Number of countries with up-to-date formal condom communications plans or strategies that link behavioral outcomes for priority groups to identified barriers (within national program documentation). | 0 | Output | 0 | 2 | 2 (Malawi and Uganda) | 4
6. Number of countries using UNAIDS Condom Needs Estimation Tool to inform condom quantification and needs-based procurement decisions | 0 | Output | 0 | 3 | 3 (Uganda, Zambia, Moz) | 3
7. Number of priority countries that are receiving technical or in-kind support from public-private partnerships developed under the SI | 0 | Output |  |  | 2 (Malawi, Moz) | 
8. Percentage of technical support recipients reporting high satisfaction with assistance provided through the SI | 0 | Output |  | 80% | 80% | 80%

## Slide 9
II. Project Architecture and Roles

## Slide 10: Implementation architecture
Global Fund Secretariat
Global Fund Country Teams
Global expert team
(Complementary BMGF investment)
Global HIV Prevention Coalition (GPC) Secretariat
GPC South-to-South Learning Network (SSLN)
Other complementary investments (eg UNFPA SRHR Support Hub, PEPFAR)
Malawi Mozambique Uganda Zambia
Country focal point/ manager
Country focal point/ manager
Country focal point/ manager
Country focal point/ manager
Continuous direct programmatic & management support
Condom Technical Support (regional specialists integrated into TSM)
Public-private innovation fund
UNAIDS Technical Support Mechanism (TSM)
Steering Group
Global Fund
Members of the Global Condom Working Group (incl. experts & civil society)
Private sector
Other countries
Technical & Managerial Hub
Global Coordinator of the Initiative
Hosted by UNAIDS
Builds & manages overall partnership
Regional Support Manager
Hosted by UNFPA
Provides direct country support
Support to priority actions and capacity-building on condom programme stewardship, last-mile distribution and innovative demand generation
Complementary support
Cross-country learning & exchange
Scopes of work driven by identified country priority needs
Oversight on SI
Oversight on country grants
Integration into global prevention response
Build regional TA capacity
Use existing TA platform
Grant to UNAIDS

## Slide 11: Roles and Responsibilities (1)
Condom Strategic Initiative
Ana, and as of May 2 Namwinga (Global),
and Rosemary (Regional)
Provides overall project management & accountability;
Supports in addressing bottlenecks that may arise;
Ensures programmatic and financial reporting is completed on time in all countries;
Provides quality assurance;
Collects & analyzes feedback on TA provided to countries;
Conducts baseline & follow-on assessments to measure progress at country level;
Liaises with MGH for TA provision;
Signs-off on deliverables after UNAIDS/UNFPA CO approval
Global and Regional Coordinators
Joel (Malawi); Sandra (Mozambique);
Wilberforce (Uganda); Lizzy (Zambia)
Liaises with NAC or MOH;
Creates and manages Task Team to advice consultants;
Manages technical assistance and consultants;
Provides TA in other areas of expertise;
Facilitates integration with treatment & other prevention initiatives happening in-country;
Leads in identifying and addressing bottlenecks;
Inputs into programmatic and financial report;
Signs-off on technical deliverables
Country Managers
Varies by country
Identifies country manager (CM) and ensures they are onboarded properly;
Ensures a supportive environment for CM with access to resources necessary to do their work;
Provides oversight of technical and management activities;
Ensures support to address bottlenecks;
Ensures programmatic and financial report in-country is completed on time;
Signs-off on deliverables after Country Manager’s approval
UNAIDS/UNFPA Country Office (CO)
Global Fund Condom SI team
Susie; Carla
Strategic Direction
Liaison with GF Country teams
Overall Oversight

## Slide 12: Roles and Responsibilities (2)
Condom Strategic Initiative
Paid for by BMGF & provided by MGH
Brian (Mozambique and Zambia); Chris (Malawi and Uganda)
Develops & disseminates best practice, tools & guidance;
Identifies resources and brokers partnerships to expand availability of quality TA and intervention support;
Delivers support remotely & in-person during execution;
Supports Global and Regional coordination in quality assurance during execution;
Mentors, coaches and capacitates Country Support Manager and regionally based consultants
Supports development of SOWs
Technical Resource (MGH)
Contract managed by TSM/Genesis; technical deliverables managed by Condom SI
Leads in carrying out the SOW;
Makes suggestions and recommendations on how to improve the outcomes of the consultancy, if applicable;
Maintains good relationships with stakeholders;
Engages promptly with Task Team
Technical Consultants
Led by Genesis - Analytics. POC varies by country
Curates roster of technical consultants;
Matches technical support needs to the right resource;
Draws and manages contract with the consultant;
Pays invoices after deliverables have been approved by Country Manager, UNAIDS/UNFPA supervisor and Global or Regional Coordinator
TSM (Genesis)

## Slide 13
III. Reality Check: How it is going and project management adjustments

## Slide 14: Small Group Discussions
Purpose: Shared understanding of challenges and what is causing them, and identify solutions
Break into two groups to identify challenges and opportunities
      Regional and Global team to join Brian
      Country teams to join Chris
~ 30 min in break out
~ 30 min in plenary
Link to Jamboard with vision and challenge exercise

## Slide 15
IV. Deep Dive: Project Management

## Slide 16: Bringing clarity to project management thru a RACI Matrix
A RACI matrix is a project management tool that aims to clarify the stakeholders on a project and their level involvement in each task.
R, A, C, I stands for:
Responsible designates the task as assigned directly to a person or team. The responsible person is the one who does the work to complete the task or create the deliverable. Every task should have at least one responsible person and could have several.
Accountable individuals delegate and reviews the work involved in a project. Their job is to make sure the responsible person or team knows the expectations of the project and completes work on time. Every task should have only one accountable person and no more
Consulted people provide input and feedback on the work being done in a project. They have a stake in the outcomes of a project because it could affect their current or future work. Not every task or milestone needs a consulted party, but the project manager should consider all possible stakeholders when creating the RACI chart and include as many consulted parties as is necessarily appropriate.
Consulted parties may be individuals on the project team who aren’t working on a given task but whose work will be affected by the outcome. They’re also often outside of the project team —even in different departments—whose work will be affected by the outcomes of the project.
Informed folks need to be looped into the progress of a project but not consulted or overwhelmed with the details of every task. They need to know what’s going on because it could affect their work, but they’re not decision makers in the process..

## Slide 17: Roles & Responsibility Matrix for the Condom SI (June 17, 2021)
Complete matrix accessible here

## Slide 18: Example of using RACI
Responsible | Accountable | Consulted | Informed
The person (singular) doing the work | Ensures (singular) work is completed according to guidance and on time | Provide input, feedback on the work | Really just informed, not consulted or overwhelmed with the details of the task
Task: Preparation of bi-annual programmatic and financial reports to The Global Fund

## Slide 19: Meeting Cadence and Structure
Meeting | Purpose | When (All times Geneva) | Who attends
Weekly coordination CMs | To share information and brainstorm solutions to challenges and concerns; share expertise and advice. | Every Wednesday: 14:00 | UNAIDS/UNFPA Condom SI Hub team: Rosemary and Ana (soon Namwinga) Country Managers (CMs): Lizzy, Wilberforce, Joel, Sandra Guests: Carla (GF) Mncedisi/Katlego (Genesis)
Bi-weekly update | To discuss progress on key milestones and opportunities for collaboration with other GF Strategic Initiatives, donors, governments, and private sector. | Every other Monday: 16:00 – 17:00 | GF Condom SI team: Susie, Carla MGH Advisors: Chris, Brian UNAIDS/UNFPA Condom SI hub team: Clemens, Adriana, Ana* (UNAIDS) and Innocent, Rosemary (UNFPA) *soon Namwinga
Monthly update | To provide progress updates to the GF’s country teams. | Starting in June, these meetings will take place once per quarter. Day and time TBD with each country team | For their respective country: Country Managers (CMs); CM Supervisors; GF Country Teams; GF Condom SI Focal point: Carla; UNAIDS/UNFPA Condom SI Hub team: Clemens, Ana*, Rosemary MGH Advisors: (Chris for Malawi and Uganda; Brian for Mozambique and Zambia) *soon Namwinga

## Slide 20
V. The Week Ahead

## Slide 21: Objectives of the Training
Co-creating and aligning on key elements critical to the successful project management and implementation of the SI;
Organizational structure at the regional and country level required to effectively and efficiently achieve the SI’s goals;
Identified processes to support implementation and enable teams to achieve their goals;
Clarity on project management requirements for the SI grant;
Developing a common understanding of critical technical areas that cut across countries and practical strategies for addressing them;
Strengthening “soft skills” in ensuring sustained engagement of stakeholders, influencing policy and funding, developing actionable scopes of work for consultants, managing consultants and following through on recommendations to ensure that recommendations are implemented;
Developing greater awareness of resources available at regional and country level and how to access them.

## Slide 22: Agenda Overview
 | Mon | Tue | Wed | Thu | Fri
AM | Welcome: Paula (UNAIDS), Susie (GF), TBD, UNFPA ESARO Icebreaker (Adriana) Objective 1 a, b, c a. SI goal & purpose b. Organizational structure c. People, roles, responsibilities (Clemens, Rosemary, Ana, Adriana) | Objective 1 d. Processes to support implementation Milestones (PF); Budget, TA plan (Ana & Rosemary) Tech Topic 3: Country Specific Design of Condom Dashboard (Chris & Joel) | Soft Skill Session 1 Performance improvement 101 Issue identification, desired/current performance, gap (Chris, Namwinga) Tech Topic 5: Demand Creation (Ana, Purvi with Paris from MBX and Amanda from PLM ) | Soft Skill Session 2 Performance improvement 101 Root cause analysis and solution design (Chris, Namwinga) Objective 4: Resources SSLN, TSM, SAT and other resources (Carla, Brian) | Soft Skill Session 3 -Influencing/ coordinating (role of TWG) and/or setting up consultancies for success Ability to advocate for funding (Brian, Rosemary) Wrap Up Susie & Clemens
PM | Tech Topic 1: CNET (Henk, Ana, Brian) Tech Topic 2: Last Mile Distribution (Brian, Wilberforce, Joel, Lizzy, James from PLM) | Tech Topic 4: Total Market Approach (Chris, Wiberforce, Brian & Rosemary) | Flexible afternoon with options for focused topics and priority planning Core management team meeting | Objective 1e: Project mgmt requirements for the SI grant (Carla, Ana., Namwinga) Country Work Planning Report back on priority action plan (Rosemary, Ana) | [Participants leave] Core management team meeting
EVE |  | Optional CNET “clinic” Henk, Brian & Ana |  | Group Dinner (important to clarify that this is optional and also self-funded) | 
Daily sessions start at 8:30 and end at 17:00 hrs. 15’ Breaks at 10:30 and 15:00. Lunch between 12:30 – 13:30 hrs

## Slide 23: Participant Lists
 | UN Members | Government and NGO PRs | Total Country Delegation
Uganda | 2 | 4 | 6
Malawi | 4 | 5 | 9
Zambia | 4 | 4 | 8
Mozambique | 3 | 5 | 8
Total: 50 confirmed participants with 4 joining online