# UNAIDS – Global HIV Prevention Campaign 2026–2028

Global-Level Campaign Pitch and Country Implementation Template/Workbook

This template follows a 12-step campaign strategy approach and is designed for the UNAIDS Global HIV Prevention Team to use when developing the 2026–2027 Global HIV Prevention Campaign and associated country-level implementation plans.

## Basic Campaign Information

Working campaign title:

- Lead for Prevention

- Commit to Prevention

- Commit and Sustaining Prevention (would go for  this)

Strapline/slogan:

Political leadership and sustainable financing to protect and expand access to HIV Prevention

Timeframe:

March 2026 – March 2028

Lead team (global / Geneva):

UNAIDS HIV Prevention team and GPC Secretariat, hosted by UNAIDS

Core partners:

Strategic partners for conceptualization of the campaign: Members of the Global HIV Prevention Coalition Steering Committee (UNFPA, WHO, Global Fund, USG, Gates Foundation, AVAC, Frontline AIDS, Multisectoral Leadership Forum reps, civil society reps)

Strategic partners, global: Global Fund, USG, World Bank, UNITAID, Gates Foundation, Medicines Patent Pool, WHO, UNFPA, UNDP, World Bank, African Development Bank, UN Women, UNICEF, UNODC, UNESCO, African Union, African CDC, SADC, ASEAN, LAC Horizontal Group, G20 Health and Finance tracks (?) SSLN, Civil society organizations and networks, especially African Women Prevention Community Accountability Board, KP networks (APCOM, MPACT, NSWP, INPUD, GATE, Youth Rise) (adapt by region), Pharmaceutical companies, marketing partners (Durex)Strategic partners in country:

Ministries of Health

Ministries of Finance / Planning

Office of the President / Prime Minister (where relevant)

National AIDS Councils / Commissions

Parliamentary health and budget committees

Local government associations

UNAIDS and UNFPA Country Offices

UN Country Teams/Resident Coordinators

Country Coordinating Mechanisms (CCMs)

Civil society organizations and networks,

Private sector (where relevant)

Technical partners:

WHO, Avenir Health, CHAI, PSI, Unitaid, FHI360, Path, DKT International, IPPF, Harm Reduction International, CAPRISA, IAS, Modelling Consortium, Harvard School of Public Health, Monash University Malaysia, Medicine Patent Pool, Reproductive Health Supplies Coalition, FP2030

Advocacy partners: AVAC, Frontline AIDS, GNP+, IPPF, Women’s and youth networks within the GPC ecosystem; Key population networks, World Council of Churches,

Any close ties with high profile persons or champions - to carry the campaign messages

Primary focus of the campaign:

- Strengthen political buy-in and visibility for prevention at global, regional and country level to secure sustainable financing for the accelerated, equitable scale-up of combination prevention and innovative HIV prevention options

Priority prevention outcomes by 2030 (linked to global targets):

Process measures/ objectives: - Senior political commitments to HIV prevention secured and implemented (e.g., ministerial statements, cabinet decisions, communiqués, or signed commitments that explicitly prioritise prevention financing and policy action, budget line on HIV prevention). - Grassroots community mobilisation strengthened: Community and civil society networks generate public demand and advocate for government leadership on HIV prevention, and to track delivery on commitments through community-led accountability mechanisms (e.g., scorecards, public reporting, social mobilisation actions) in X priority countries. - Policy reform agenda initiated (explicit national commitment to remove policy/legal bottlenecks to equitable prevention access, including for young people and key populations). Outputs: - Updated/adopted national HIV prevention strategy, grounded in human rights, equity and community leadership, with clear scale-up pathways for combination and innovative prevention options. - Fully costed investment plans for HIV prevention inclusive of community-led prevention approaches - Policy/regulatory integration outputs, including prevention options incorporated into national guidelines and essential service packages; clarified regulatory pathways; and implementation guidance issued). - Increased visibility of HIV prevention as a political priority, including prevention featured in high-level moments and sustained coverage across major media and digital platforms, supported by partner amplification. Outcomes: - Political leadership institutionalized: HIV prevention is consistently prioritised in national political agendas, with sustained senior-level accountability and cross-government ownership (health, finance, planning), reflected in regular policy review mechanisms, public reporting, and integration into national development and health strategies in X high-burden countries. - Sustainable financing secured: By ...., X countries allocate ≥20% of total HIV financing to prevention, reflected in approved budgets and expenditure frameworks. - Enabling policy environment strengthened: By ..., X countries have removed key legal, regulatory, and policy barriers to equitable access and scale-up of combination and innovative HIV prevention, including integration into national guidelines, essential service packages, and streamlined regulatory pathways. Longer term, impact level outcomes: · 90% people in need use prevention options by 2030 · 90% reduction in new HIV infections from 2010 to 2030 o Prevention options: 20m using PrEP options, 20b condoms, etc. (targets from the framework) o Financing: Over 20% domestic HIV funding allocated for prevention o Coverage: 67m women & girls + 36m boys & men in locations with high HIV burden reached with combination prevention

## STEP 1: Identify and analyse your issue and your context

### Global campaign issue (2026–2028)

Despite significant progress in HIV prevention, HIV prevention is at a crossroads. The world faces complex geopolitical and financial challenges, rising vulnerability and inequalities that have already severely impacted efforts to maintain sustainable HIV prevention programmes, with millions more who risk losing access to lifesaving HIV services, while vulnerable communities face rising HIV infections. Lack of funding: The funding crisis of 2025, triggered by reductions in donor funding and the abrupt halt in US government funding through PEPFAR, USAID, have directly impacted HIV prevention programmes in countries. Political will and prioritization: In light of threats, conflicts and humanitarian situations around the world, many governments are diverting funding away from health and HIV programming to defence, military spending, intelligence, etc.

    - Problem statement (global level):

Describe the core problem this campaign will address in 1–2 concise paragraphs.

Problem: As a result of drastic shifts in political and economic landscapes, funding and political support for HIV prevention programmes have been decimated, severely impacting continuity of HIV prevention programming, access to HIV prevention options, etc., which are reversing progress and can prevent us from achieving the 2030 prevention targets. Despite major scientific advances and proven prevention tools, HIV prevention is being progressively deprioritised in political decision-making at global and country levels. In an increasingly crowded political agenda shaped by security concerns, economic pressures, and multiple competing crises, prevention has slipped down priority lists, resulting in weakened political leadership, unstable financing, and delayed policy action. These are not inevitable external forces, but the result of choices about where political attention, public resources, and regulatory effort are directed. This erosion of political prioritisation is already undermining the continuity and scale-up of HIV prevention programmes, constraining investment in prevention, and slowing the integration of new and existing prevention options into national policies and delivery systems. Without renewed political leadership, sustainable financing, and enabling policy environments, the world risks losing momentum in prevention and falling further off track from the 2030 HIV prevention targets. The core problem this campaign addresses is the political and policy neglect of HIV prevention — and the need to re-establish prevention as a sustained political, financing, and policy priority. Solution: Create political buy-in for expansion/sustaining of HIV prevention and appeal to donors and secure existing/new funding sources/donors for fully financed, sustainable HIV prevention programmes and innovations. Actions: High-level advocacy with Heads of State, celebrities, influencers, Ministers of Health/Finance, philanthropic figures, key stakeholders and community for community demand generation and political movement; Political and financial commitments – signatories announced at a high-level event, with high visibility and recognition; Advocacy (including virtual/social media platforms and more formal events) for shared financing models that integrate domestic, global, and innovative funding sources, framing HIV prevention as a high-return investment.

1.1.2 Why now (2026–2027 window):

Summarise key opportunities and threats in this period (e.g. scientific, political, funding, social, and rights context).

The global HIV prevention response is at a critical inflection point. Scientific and technological advances — including long-acting and user-controlled prevention options, improved service delivery models, and stronger data systems — create a genuine opportunity to accelerate prevention impact and expand user choice. These innovations, combined with growing evidence of the cost-effectiveness of prevention and emerging opportunities for market shaping and pooled procurement, strengthen the investment case for sustained prevention financing. At the same time, the political and financing environment has become more fragile. Declining donor funding and recent funding disruptions, together with constrained domestic fiscal space and rising public spending pressures on security, humanitarian response, climate resilience, and economic stabilisation, are increasing the vulnerability of prevention programmes. Prevention is often deprioritised in political agendas relative to more immediate or visible pressures, weakening accountability and long-term investment incentives. Social and legal barriers continue to constrain equitable access to prevention, particularly for key populations and young people, while shrinking civic space in some contexts undermines community-led delivery and accountability. Environmental and humanitarian shocks, including conflict and climate-related events, disrupt service continuity, increase displacement and vulnerability, and divert political attention and resources toward emergency response. This convergence of high scientific opportunity and rising political, financial, and operational risk makes this a decisive moment. Without renewed political leadership and sustainable financing, new prevention technologies risk remaining underutilised, inequities may widen, and progress toward the 2030 prevention targets may stall or reverse. Conversely, timely political action can stabilise financing, unlock scale-up, protect access, and translate scientific advances into population-level impact.

### 1.2 External context summary (PESTLE/trends)

Provide a summary of the broader context using the PESTLE framework.

| Political: Aid volatility and geopolitics: funding freezes/cuts to international HIV assistance are disrupting prevention and community-led delivery, with some countries still heavily donor-dependent for core services. Global governance “moments” to leverage: the concept note’s emphasis on using high-level diplomacy moments (AU/G20/UNGASS) to secure shared commitments fits the current need for political “lock-in” of prevention financing and access. Policy tension: prevention is often the first. line-item cut (vs treatment), so global political prioritisation must explicitly protect prevention budgets and supply chains. Key opportunities: Global and regional political moments (e.g., UNGASS, AU Summit, G20 discussions) provide windows to elevate prevention as a political priority and secure visible leadership commitments and peer accountability. Growing recognition of sustainability, transition, and domestic financing creates space to reposition prevention as a long- term political and fiscal investment rather than a donor-dependent programme. Regional leadership platforms (AU, SADC, ASEAN, LAC) offer opportunities to reinforce collective political momentum and norm-setting around prevention prioritisation. Key threats: Prevention is increasingly deprioritised in political agendas as governments focus on security, humanitarian response, and short-term political pressures. Short political cycles and competing national priorities limit incentives for long-term prevention investment and long-term system reform.Weak political accountability mechanisms allow prevention budgets to be reallocated without sustained scrutiny or protection.. |  |
| --- | --- |
| Economic - Prevention financing fragility: donor declines, limited domestic space are materially reducing prevention access (including PrEP). - Macro-fiscal squeeze: public debt servicing can vastly exceed health allocations (e.g., noted for western/central Africa), constraining countries’ ability to absorb donor reductions. - The concept note’s “shared responsibility” model is economically coherent: domestic coverage for higher-income settings, pooled/global mechanisms to subsidise LIC access align with the reality of constrained fiscal space and the need for lowest-possible prices. Key opportunities: Increasing evidence on the long-term cost savings of prevention relative to treatment strengthens the argument for protecting prevention investments in fiscally constrained environments. Many countries are actively pursuing tax reform, efficiency gains, and health financing reforms, creating entry points to anchor prevention more firmly in domestic budgets rather than relying predominantly on external funding. Blended finance, pooled procurement, and regional market-shaping mechanisms can reduce unit costs and improve affordability of new prevention technologies over time. Key threats: Declining donor funding and recent funding disruptions have directly reduced available resources for HIV prevention programmes. Public spending and political attention are increasingly being redirected toward security and defence, humanitarian response, climate-related shocks, and macroeconomic stabilisation, reducing fiscal space for sustained investment in HIV prevention. Constrained domestic budgets, debt servicing, and inflation limit governments’ ability to absorb funding gaps.. |  |
| Social/cultural & gender norms - Trust and stigma dynamics: the WAD report highlights high levels of concealment and discrimination in some contexts and explicitly positions community groups as trusted actors—critical for demand generation and sustained prevention use. - Youth and key/priority populations: the concept notes focus on ages 15–39, and people-centred messaging is strategically aligned with where prevention impact and demand-generation efforts are often most needed. Key opportunities: Youth leadership, community mobilisation, and digital engagement platforms offer new channels to amplify prevention demand and political visibility. Growing global attention to gender equality and social inclusion creates opportunities to strengthen rights-based prevention narratives. Key threats: Persistent stigma, criminalisation, and shrinking civic space continue to undermine access to prevention services for key populations. Misinformation and declining trust in public institutions can weaken public support for prevention investment and uptake of new prevention options.. |  |
| Technological - A “new era of choice” but rollout complexity: long-acting prevention tools can reduce adherence barriers, but require regulatory pathways, financing, integration into national strategies, and supply planning (plus a mix of options, not substitution). - Global commodity pooling and price negotiation are presented as core enabling technologies/market-shaping mechanisms (not just “procurement admin”). Key opportunities Long-acting and user-controlled prevention technologies offer the potential to reduce adherence barriers, improve persistence, and expand user choice, particularly for populations that face challenges with daily or clinic-based prevention. Digital health tools, differentiated service delivery models, and integration with sexual and reproductive health services can improve reach, continuity of care, and system efficiency if supported by enabling policy and financing.Advances in modelling, and programme analytics enable better targeting of prevention investments, supporting stronger investment cases and accountability for impact. Key threats Without timely political commitment, regulatory readiness, and sustainable financing, new prevention technologies risk remaining confined to pilots or limited roll-out rather than achieving population-level impact. Workforce capacity, supply chain limitations, regulatory bottlenecks, and service delivery infrastructure may slow effective integration of new prevention options without political prioritisation. Lack of coordination across donors, manufacturers, and implementers can lead to duplication, inefficiencies, and slow market maturation. Unequal digital access, data protection concerns, and misinformation can limit the effectiveness of digital-enabled prevention approaches.. |  |
| Legal / policy |  |
| - Punitive laws are worsening: many countries criminalise aspects of sex work, drug possession, same-sex relations and transgender people; HIV criminalisation exposure remains widespread—directly depressing testing, disclosure and service uptake. - Shrinking civic space: increasing restrictions on civil society matter because donors supply a large share of “societal enablers” funding (human rights, stigma reduction, legal literacy, etc.). Key opportunities Many countries have national HIV prevention road maps or strategies aligned with the , creating a policy basis to strengthen prevention prioritisation and financing if political leadership is mobilised. Increasing focus on sustainable financing, domestic resource mobilisation, and transition planning provides an opportunity to embed prevention more firmly in medium-term policy and budget frameworks. Some countries are advancing regulatory reforms and regional harmonisation mechanisms that can accelerate approval and adoption of new prevention technologies when politically supported. Key threats Criminalisation of key populations, restrictive age-of-access laws, and discriminatory policies continue to limit access to prevention services and reduce the effectiveness of prevention investments. Increasing restrictions on NGOs, community organisations, and advocacy activities weaken accountability mechanisms and community-led prevention delivery. Lengthy approval processes and fragmented regulatory systems can delay introduction and scale-up of new prevention technologies without strong political prioritisation. Lack of coordination between health, justice, education, and finance policies can dilute prevention impact and complicate financing alignment.. |  |
| Environmental Climate and conflict shocks crowd out prevention: the report explicitly notes finite domestic resources being diverted to conflict/natural disasters and the huge scale of climate adaptation financing needs, both of which squeeze fiscal space for prevention. Key opportunities Increased focus on crisis preparedness (for climate shocks and conflict-related disruption) creates entry points to strengthen resilient HIV prevention delivery models—especially community-led and decentralised approaches.Expanding differentiated service delivery, multi-month dispensing where relevant, mobile/outreach platforms, and flexible delivery models can protect prevention access during displacement, infrastructure disruption, or insecurity. Humanitarian coordination mechanisms can create opportunities to integrate HIV prevention into broader crisis response packages (health, protection, SRH), improving continuity for affected populations. Key threats Conflict and insecurity can interrupt outreach, close facilities, restrict movement of communities and health workers, and reduce the reach of prevention services—especially for key populations and mobile groups. Conflict and climate shocks drive displacement and instability, making consistent prevention access harder and increasing risk exposure for vulnerable populations. Damage to infrastructure and transport constraints can delay prevention commodities and increase delivery costs, undermining continuity and scale-up. During conflict or environmental emergencies, budgets and political focus are often redirected toward security and humanitarian response, squeezing fiscal space for sustained prevention investment.. |  |

### 1.3 Country-level implementation context (To be completed during regional/country adaptation)

For each priority country, briefly summarize the prevention context.

| Country | Main prevention gaps | Key political & funding dynamics | Existing prevention platforms (PrEP, condoms, etc.) | Opportunities & constraints 2026–27 |
| --- | --- | --- | --- | --- |

STEP 2: Identify your long- and short-term changes

### 2.1 Long-term change / Goal

Eventually: - HIV new infections are significantly reduced - Goals of the new HIV response are achieved in terms of new infections, deaths, HIV-related stigma and discrimination

Global goal (impact statement):

Describe the long-term change this campaign contributes to (e.g. reduction in new HIV infections by 2030, equitable access to HIV prevention tools, etc.).

Programmatic: - HIV incidence: Reduce from 1.3 m per year new infections to less than 200 000 per year by 2030 (90% reduction in new HIV infections by 2030 from 2010 baseline) - 90% of people in need of HIV prevention use HIV options of their choice.

2026–2027 campaign objectives (SMART)

List 3–5 specific, measurable objectives for the 2026–2028

| Objective # | Objective statement (WHO does WHAT by WHEN) | Indicator(s) | Baseline (2026) | Target by early 2028 |
| --- | --- | --- | --- | --- |
| 1 Institutionalise political leadership for HIV prevention | By early 2028, the campaign, working with national governments, regional bodies, and civil society partners, will secure formal senior-level political commitments and embed HIV prevention prioritisation into national policy and accountability mechanisms in at least X high-burden countries. | Number of countries with documented senior-level political commitments (ministerial statements, cabinet decisions, national communiqués). Number of countries with prevention explicitly referenced in national development plans, health strategies, or medium-term policy frameworks. Number of countries reporting regular political review mechanisms for prevention (e.g., annual reporting, parliamentary or cabinet review). | Less than half of priority countries have senior level political commitments on Prevention Less than half of priority countries have prevention explicitly referenced in national development plans, health strategies or medium-term policy frameworks. Less than half of priority countries have mechanisms for reporting regularly political review for prevention | More than 90% of priority coutries have senior level political commitments on Prevention More than 90% of priority countries have prevention explicitly referenced in national development plans, health strategies or medium-term policy frameworks. More than 90% of priority countries have mechanisms for reporting regularly political review for prevention |
| 2 Secure sustainable financing prioritisation for prevention | By end-2027, the campaign, in collaboration with national governments, financing partners, and multilateral institutions, will increase domestic prioritisation of HIV prevention, with at least X countries allocating ≥20% of total HIV budgets to prevention. | Number of countries allocating ≥20% of total HIV budgets to prevention (approved budgets or expenditure frameworks). Number of countries showing year-on-year increase in prevention budget share compared to 2025 baseline. Evidence of multi-year budget protection or co-financing mechanisms. | Less than 50% of priority countries allocate more than 20% of total HIV budget to prevention Less than 50% of priority countries show year-on year increase in prevention budget shared compared to 2025 baseline. | More than 90% of priority countries allocate more than 20% of total HIV budget to prevention. More than 90% of priority countries show year-on year increase in prevention budget shared compared to 2025 baseline. |
| 3 Enabling policy and regulatory environments strengthened | By end-2027, the campaign, together with national authorities, regulators, and technical partners, will support the adoption or reform of policy and regulatory frameworks in at least X countries to enable timely approval, integration, and scale-up of combination and innovative HIV prevention options. | Number of countries integrating new prevention options into national guidelines and essential service packages. Number of countries with clarified or streamlined regulatory pathways for prevention products. Number of countries adopting implementation guidance for scale-up of long-acting or innovative prevention tools. Number of countries with legal and policy reforms that dismantle barriers to accessing HIV prevention for underserved populations (e.g., youth, migrants, mobile populations, key populations, etc.) | Less that 50% of priority countries integrate new HIV Prevention options into national guidelines and essential package More than 90% of priority countries have clarified or regulatory pathways for prevention products Less than 50% of priority countries have adopted implementation guidance for scale-up of long-acting or innovative prevention tools Less than 50% priority countries have legal and policy reforms that dismantle barriers to accessing HIV prevention for underserved populations. | More than 90% of priority countries integrate new HIV Prevention options into national guidelines and essential package More than 90% of priority countries have clarified or regulatory pathways for prevention products More than 90% of priority countries adopt implementation guidance for scale-up of long-acting or innovative prevention tools More than 90% priority countries have legal and policy reforms that dismantle barriers to accessing HIV prevention for underserved populations. |
| 4.Political visibility and community accountability strengthened | By end-2027, the campaign will strengthen public and community-led accountability for HIV prevention commitments by establishing or supporting community monitoring and advocacy platforms linked to national prevention priorities in at least X countries. | Number of high-level global/regional political moments featuring prevention commitments (UN, AU, regional blocs). Number of major media placements and digital reach metrics. Number of countries with operational community-led accountability mechanisms (scorecards, monitoring platforms, advocacy coalitions). |  | More than 90% of high-level global/regional political moments featuring prevention commitments |

### Country-level results cascade (To be completed during country adaptation)

For each priority country, define up to 3 country-level objectives aligned with the global objectives.

| Country | Objective 1 (prevention coverage/access) | Objective 2 (policy/financing) | Objective 3 (community/demand/equity) |
| --- | --- | --- | --- |

## STEP 3: Identify and analyse your stakeholders

### 3.1 Global decision-makers / primary targets

List key institutions and specific roles that must make decisions for this campaign to succeed.

| Target (institution and role) | Current position/interest | Power & influence (H/M/L) | What could move them towards our position? | Who influences them? |
| --- | --- | --- | --- | --- |
| Heads of state | Generally aware of HIV as a public health issue but do not consistently prioritise prevention; focus often diverted to security, economy, and political pressures. | H | Regional and global visibility; linking HIV prevention to development, economic stability, and political legacy; peer pressure from regional bodies (AU, SADC). | Regional blocs (AU, SADC, EAC), First Lady/Spouse offices, UN leadership, major donors. |
| MOH, NAC | Supportive of prevention in principle; often constrained by limited budgets and competing health priorities. | H | Strong political directives; technical support for guideline updates; evidence on effectiveness of new prevention options; pressure from communities and donors | National AIDS Councils, WHO, UNAIDS country offices, technical partners. |
| Ministry of Finance | Focused on fiscal stability and often view HIV prevention as donor-funded; cautious of long-term recurrent costs. | High | Evidence of cost-effectiveness and long-term savings; multi-year financing plans; regional or global recognition; clear economic framing of prevention. | Heads of State, International Financial Institutions (World Bank), Global Fund, Ministry of Health. |
| Regional Political Bodies (AU, SADC, EAC, ECOWAS, ASEAN, LAC) | Supportive at high level, but prevention competes with many regional priorities. | Medium | Regional declarations; peer accountability mechanisms; leadership from influential member states; strategic framing around health security and development. | Heads of State, regional secretariats, UN agencies. |
| Civil society and Community led Societies | Highly motivated but face shrinking civic space and resource constraints. | High | Inclusion in national decision-making; funding for community-led monitoring; political openings; visible policy wins. | Media, international donors, Parliament, MoH, NACs. |

### 3.2 Allies, opponents, swing actors

| Stakeholder group | Affected by issue? (Y/N) | Influence on decisions (H/M/L) | Current stance (ally / neutral / opponent) | Our strategy (ally, shift, contain, etc.) |
| --- | --- | --- | --- | --- |
| MOH | Y | High | Ally | Provide technical evidence, support guideline updates, build joint advocacy for financing and political prioritisation. |
| Ministry of Finance/Planning | Y | High | Neutral | Shift — frame prevention as an economic investment; use cost-effectiveness, long-term savings, and peer pressure to secure budget commitments. |
| Regional Political Bodies (AU, SADC, EAC, ECOWAS) | Y | Neutral | Ally | Ally — use regional declarations and peer accountability platforms to elevate national commitments. |
| Global Fund, World Bank, PEPFAR/USG, UNITAID | Y | High | Ally | Ally — coordinate investment frameworks, demonstrate country readiness, mobilise shared financing approaches. |
| Civil Society & Community-Led Organisations (youth, KP networks, women’s groups) | Y | High | Ally | Ally — strengthen community monitoring, advocacy, demand generation; amplify political commitments and accountability. |

### 3.3 Country-level stakeholder snapshot (To be completed during country specific adaptation)

For each country, briefly summarise key government actors, community & civil society, implementing partners, private sector, and opponents.

| Country | Key stakeholder notes (bullet points) |
| --- | --- |

STEP 4: Develop your theory of change

### 4.1 Visual theory of change (global)

CAMPAIGN INPUTS & ACTIVITIES (2026–2027) - High-level political advocacy (Heads of State, Ministers of Health & Finance) - Financing advocacy and market shaping for prevention commodities - Policy and regulatory readiness support - Community mobilisation and accountability mechanisms - Strategic communications and media engagement

IMMEDIATE OUTPUTS - Senior political commitments to HIV prevention secured - Prevention elevated in global, regional, and national political agendas - Costed national HIV prevention strategies and investment plans - Prevention integrated into national policies, guidelines, and essential service packages - Community-led monitoring and accountability platforms operational

SHORT-TERM OUTCOMES - Increased political visibility and prioritisation of HIV prevention - Improved coordination across health, finance, planning, and regulatory sectors - Initial reallocation or protection of national budgets toward prevention - Accelerated regulatory and policy readiness for combination and innovative prevention options

INTERMEDIATE OUTCOMES (by 2028) - Institutionalised political leadership for HIV prevention - ≥20% of national HIV budgets allocated to prevention in priority countries - Enabling legal, regulatory, and policy environments strengthened - Scaled and equitable access to combination HIV prevention options

LONG-TERM IMPACT (by 2030) - 90% reduction in new HIV infections (from 2010 baseline) - 90% of people in need using HIV prevention options of their choice - Sustainable, resilient, and equitable HIV prevention systems

### 4.2 Narrative theory of change

Describe in 1 page or less how your activities lead to the intended changes, including key assumptions.

The Global HIV Prevention Campaign (2026–2028) is premised on the understanding that sustained reductions in new HIV infections will not be achieved through technical solutions alone, but through deliberate political, financial, and policy choices that enable prevention to be delivered at scale and with equity. The campaign therefore focuses on shifting HIV prevention from a vulnerable, often deprioritised programme area into an institutionalised political and financing priority at global, regional, and country levels.

The campaign’s activities combine high-level political advocacy, financing and market-shaping engagement, policy and regulatory readiness support, community mobilisation, and strategic communications. Through targeted engagement with Heads of State, Ministers of Health and Finance, regional political bodies, and global financing institutions, the campaign generates visible senior-level political commitments and elevates prevention within national and international agendas. In parallel, financing advocacy and shared-responsibility approaches support the development of costed national prevention strategies, protect prevention budget lines, and catalyse domestic and co-financing commitments. Policy and regulatory support accelerates the integration of combination and innovative prevention options into national guidelines, essential service packages, and regulatory pathways, while strategic communications and community-led accountability mechanisms sustain public and political pressure to deliver on commitments.

These activities are expected to produce short-term changes, including increased political visibility of prevention, improved cross-government coordination, initial budget reallocations or protections for prevention, and greater regulatory readiness. Over time, these shifts lead to intermediate outcomes: institutionalised political leadership for HIV prevention, sustained domestic financing with at least 20% of HIV budgets allocated to prevention in priority countries, strengthened enabling legal and policy environments, and scaled, equitable access to combination prevention options. Together, these outcomes contribute to long-term impact by 2030, including a 90% reduction in new HIV infections, widespread use of prevention options by people in need, and resilient, sustainable HIV prevention systems.

This Theory of Change rests on several key assumptions: that sustained advocacy and peer accountability can influence political prioritisation; that financing commitments translate into approved budgets and expenditures; that regulatory and policy reforms are accompanied by sufficient implementation capacity; and that communities and civil society are meaningfully engaged and able to hold decision-makers accountable for results.

### 4.3 Country-level paths to change ((To be completed during country specific adaptation)

For each priority country, summarise the path to change.

| Country | 2026–27 outcomes | Key behaviour/practice changes | Key campaign contributions |
| --- | --- | --- | --- |

STEP 5: Identify and analyse your audiences

### 5.1 Priority audiences (global)

Identify the main audience segments this campaign needs to reach and influence.

| Audience segment | Why strategic? | What they know/believe now | Their best reason to say “NO” | What might move them? |
| --- | --- | --- | --- | --- |
| Heads of State / Government & Senior Political Leaders | They set national political priorities, influence budget allocations, and can elevate prevention across government sectors. Their public commitments shape national and international signals. | They generally recognise HIV as a health issue, but may view prevention as a sensitive matter given the stigma around it or a technical matter for health ministries rather than a cross-government political priority. | Competing political pressures (security, economy, elections), limited visible short-term political returns from prevention, and reluctance to commit resources amid fiscal constraints. | Clear framing of prevention as a national development, economic, and stability investment; regional peer leadership; reputational incentives; and visible international recognition of leadership. |
| Ministers of Finance / Planning & Budget Authorities | They control fiscal space, approve medium-term expenditure frameworks, and determine sustainability of prevention financing. | They often see HIV prevention as donor-supported and they are likely to put money into sectors that show quick, visible economic returns (like infrastructure, energy, industry, big projects), and/or are politically attractive or popular with voters, parliament, or powerful interest groups, | Budget ceilings, debt servicing, inflation pressures, and concern about long-term recurrent costs from new technologies. | Evidence on cost-effectiveness and long-term treatment cost avoidance, predictable co-financing arrangements, and integration of prevention into broader health and development financing frameworks. |
| Global financing and development partners (Global Fund, World Bank, bilaterals, foundations) | They shape availability and predictability of prevention financing and influence market-shaping mechanisms and country co-financing policies. | They support prevention in principle but face competing global priorities and may prioritise treatment and health systems strengthening. | Limited budgets, shifting global crises, and concern about country readiness to absorb and sustain prevention investments. | Clear political commitment signals from countries, alignment with sustainable financing frameworks, coordinated investment strategies, and strong implementation and accountability plans. |
| Policy and regulatory authorities (health ministries, regulators, normative agencies) | They determine whether prevention technologies are approved, included in guidelines, and delivered through national systems. | They recognise innovation potential but may be cautious about system readiness, safety, costs, and operational complexity. | Regulatory risk aversion, limited implementation capacity, and uncertainty about financing sustainability. | Political mandates to prioritise prevention, technical support for regulatory and guideline processes, and predictable financing signals that justify system adaptation. |
| Regional political and economic bodies (AU, SADC, ASEAN, LAC platforms) | They provide political legitimacy, enable peer accountability among Member States, and influence regional coordination on financing, policy harmonisation, and access to new prevention technologies. | They recognise HIV as a regional development and health issue, but prevention competes with multiple political and economic priorities. | Limited mandate over national budgets, and crowded regional agendas | Clear alignment with regional development and health strategies, leadership from influential Member States, and opportunities to demonstrate regional solidarity and political leadership on global platforms. |
| Communities and key populations | They are most affected by gaps in prevention access and are essential for generating demand, monitoring service delivery, and holding leaders accountable for commitments. | They experience prevention service disruptions and policy barriers directly and are often sceptical that political commitments will translate into real change. | Advocacy fatigue, shrinking civic space, and limited trust in political processes. | Meaningful inclusion in decision-making, visible political openings, support for community-led accountability mechanisms, and tangible service improvements. |

### 5.2 Country-level audiences (To be completed during country adaptation)

| Country | Audience segment | Key characteristics/values | Trusted messengers | Notes |
| --- | --- | --- | --- | --- |

## STEP 6: Develop your messages for critical audiences

### 6.1 Core internal proposition

Draft one internal proposition that all messaging should align with.

HIV prevention will not get back on track through technical solutions alone. Without renewed political leadership, sustainable financing, and enabling policy environments, scientific innovation cannot translate into equitable access at scale. The next two years are a decisive window to re-establish prevention as a political, financial, and policy priority and keep the world on course for the 2030 HIV prevention targets.

### 6.2 Global top-line messages

List 3–5 top-line messages for the campaign.

1. HIV prevention is falling behind not because we lack tools, but because it is no longer being prioritised in political decision-making. Renewed political leadership is essential to protect progress and accelerate access to prevention.

2. Sustained investment in prevention saves lives and reduces long-term treatment costs. Prioritizing prevention is not only a moral imperative, but one of the smartest public health investments that governments can make.

3. Scientific breakthroughs will not reduce infections unless financing, policies, and service systems are ready to deliver prevention at scale. Innovation must be matched by political commitment and enabling policy environments.

4. Populations and locations with the highest HIV burden continue to face the greatest barriers to prevention. Achieving equitable access requires political choices that remove legal, financial, and policy obstacles to services.

5. Decisions taken in 2026-2027 will determine whether the world accelerates toward the 2030 prevention targets or remain off track. This is the moment to act decisively on leadership, financing, and policy.

### 6.3 Message matrix (global + country adaptation)

| Audience | Global message (headline + 2–3 bullets) | Emotional hook/story | Example adaptation at the country level |
| --- | --- | --- | --- |
| Politicians- Heads of state/Government | - Political leadership is the decisive factor that will determine if HIV prevention succeeds by 2030. - Prevention is falling behind not because of science, but because it is not politically prioritized. - Your leadership can protect national progress, save future treatment costs, and strengthen national stability | A young woman describing how new prevention tools allowed her to stay HIV-free because leaders prioritised access and how many others will lose opportunities if leadership falters. | Kenya has led Africa in adopting HIV innovations before. A renewed presidential commitment in 2026 can safeguard gains despite financing shocks and ensure young people access prevention options across all counties. |
| Ministry of Finance and Planning | - Investing HIV prevention now saves your government money later. - Every dollar invested in prevention saves multiple dollars in long-term treatment costs. - Prevention funding protects the future fiscal stability of the health sector. - Shared financing models reduce pressure on domestic budgets while sustaining impact. | A finance officer describing the rising cost of treatment over 10–15 years and how prevention of investments earlier could have reduced the need for higher recurrent costs. | Integrating HIV prevention into the Medium-Term Expenditure Framework reduces future ART liabilities and supports Uganda’s demographic dividend goals. |
| Global Financing Partners (GFATM, PEPFAR/USG, World Bank, Unitaid) | - Global and domestic financing alignment is critical to sustain prevention scale-up. - Coordinated investment prevents duplication and maximizes impact. - Country political signals unlock domestic co-financing. - Prevention innovation requires sustained donor partnership during scale-up. | A community-led organisation sharing how donor-supported PrEP delivery allowed thousands to stay HIV-free but expressing fears of losing access due to shrinking donor budgets. | Example; SADC countries have signaled political commitment; global partners can now reinforce this by protecting prevention allocations in 2026–2027 grant cycles. |
| Community & Key Population Networks | - Your leadership makes prevention real and accountable. - Community voices drive demand, identify service gaps, and hold leaders to commitments. - Community-led accountability is essential to sustain progress during crises. - Prevention options must reflect lived experience and user preference. | A young advocate describing how community monitoring of PrEP availability forced local leaders to solve chronic stockouts. | Example in Nigeria, community networks can document and publicly report gaps in adolescent girls’ access to prevention, strengthening state-level accountability for commitments. |
| Media & Public Influencers | - Your storytelling shapes political will for HIV prevention. - Media visibility drives public pressure for leadership and financing. - Accurate reporting reduces stigma and increases prevention of uptake. - Spotlighting prevention champions influences elite decision makers | A journalist describing how highlighting a community PrEP success story changed local government attitudes toward HIV prevention funding. | Showcasing Ghanaian innovators and youth-led prevention initiatives can build national pride and political momentum for scale-up. |

## STEP 7: Choose your tactics, tools, and activities

### 7.1 Global tactics overview

Select and describe the main tactics the campaign will use.

| Tactic | Objective(s) it mainly serves | Key global activities (2026–27) | Lead unit/partners |
| --- | --- | --- | --- |
| High-level political advocacy & leadership engagement | Institutionalise political leadership Secure senior-level commitments Protect prevention prioritisation in national agendas | Targeted engagement with Heads of State and Ministers of Finance/Health at major political moments (UNGA, AU Summit, G20, regional ministerial meetings) Bilateral briefings for political leaders in priority countries High-level leadership dialogues linked to global and regional forums Public commitment moments and recognition of political champions | UNAIDS Executive Office and Regional Support Teams UNFPA Executive Office UNAIDS Country Directors Regional bodies (AU, SADC, ASEAN, LAC platforms) |
| Financing advocacy, shared responsibility, and market shaping | Increase domestic prioritisation of prevention financing Advance shared financing plan Support affordable and sustainable scale-up of prevention innovations | Develop epidemiology-based prevention needs estimates and country investment targets to inform financing decisions. Develop and promote a global financing matrix and shared financing plan, clarifying domestic and international responsibilities. Conduct targeted health diplomacy with Ministries of Finance, development partners, and multilateral institutions to secure financing commitments. Organise financing-focused side meetings and dialogues at AU Summits, G20 meetings, and UNGASS 2026. Establish and track a virtual pool of financing commitments for prevention innovation access. Support collective price negotiation and market-shaping efforts for long-acting and other high-impact prevention products. | UNAIDS Data team/sustainability team Global Fund, World Bank, bilateral donors Modelling and market shaping partners In country financing decision makers |
| Policy and regulatory readiness support | Strengthen enabling policy and regulatory environments Accelerate access to combination and innovative prevention options | Support for guideline updates and regulatory readiness for new prevention technologies Regional policy dialogues on regulatory harmonisation and procurement pathways Technical assistance for integration of prevention into national essential service packages and strategies Dissemination of implementation guidance and best practices | WHO, UNAIDS, National regulatory authorities Technical partners (FHI360, PATH, CAPRISA, IAS) |
| Community mobilisation and accountability mechanisms | Strengthen accountability for political and financing commitments Sustain political and public pressure for prevention prioritisation Increase demand and social visibility for prevention options | Global and regional youth mobilisation campaigns focused on choice, empowerment, and access to new and existing prevention options. Partnerships with youth-led and community-led organisations to amplify prevention narratives and political demands. Support to community-led monitoring, scorecards, and public tracking of political and financing commitments on prevention. Youth and community participation in high-level political moments and regional platforms to reinforce accountability. Digital storytelling and peer-led advocacy linked to national and regional policy dialogues. | Youth and community networks (e.g. Youth Rise, Teenergizer, GNP+, NSWP, INPUD, Frontline AIDS) UNAIDS community and human rights teams |
| Strategic communications & public mobilisation to build political momentum | Elevate political visbiity of HIV prevention Build public and elite opinion in support of access to prevention innovations Reinforce advocacy and accountability efforts | Global virtual campaign launch featuring high-profile opinion leaders and champions. Media briefings with global and regional outlets, with coordinated country-level replication. Editorial placements and opinion pieces in major global and regional media. High-impact scientific and policy commentary (e.g. Lancet or equivalent platforms). Targeted social media outreach to political influencers, cultural leaders, and youth networks. Coordinated partner amplification using common messaging and campaign branding. | UNAIDS Communications Media partners and digital platforms Campaign champions and influencers GPC communications focal points |

### 7.2 Country-level implementation activities (TBD during Country adaptation)

| Country | Priority tactic(s) from the global list | Key campaign activities in the country (2026–27) | National & community partners | Support needed from the global team |
| --- | --- | --- | --- | --- |

## STEP 8: Resource mobilising plan

### 8.1 Resources to run the campaign (internal)

|  | Cost category | 2026 budget (US$) | 2027/28 budget (US$) | Notes/assumptions |
| --- | --- | --- | --- | --- |
| 1 | Coordination and content analytics | $20,000 | $10,000 | LOE for campaign manager, comms lead, and data support. |
| 2 | Communication and branding | $15,000 | $5000 | Design, branding assets, video content, social media materials. |
| 3 | High level advocacy and engagement | $20,000 | $20,000 | Travel support, briefing packs, ministerial roundtables, and side events. |
| 4 | Technical workshops and TA support | $9000 | $5000 | Regional workshops, regulatory readiness sessions. |
| 5 | Digital Campain infrastructure | $8000 | $2000 | Website updates, analytics tools, virtual launch hosting. |
| 6 | Monitoring, Evaluation and Reporting | $5000 | $5000 | Dashboarding, quarterly progress tracking, documentation |
| 7 | Administration and Operations | $4000 | $2000 | Project management, subscriptions, printing, and logistics. |
|  | TOTAL | $81,000 | $49,000 | $130,000 |

### 8.2 Resources the campaign seeks to unlock (external)-  TBD

| Funding stream | Target amount (by 2030; note 2026–27 milestones) | Mechanism (domestic / GF / other) | Campaign actions to catalyse this |
| --- | --- | --- | --- |

### 8.3 Country-level financing and resource mapping (TBD)

| Country | Current domestic HIV prevention spending | Key funding gaps for prevention | Opportunities to leverage GF/PEPFAR/other | Role of campaign in unlocking/protecting resources |
| --- | --- | --- | --- | --- |

## STEP 9: Monitoring, evaluation, and impact assessment

### 9.1 Monitoring framework (campaign delivery)- (Please refer above)

| Specific change/result | Indicator | Data source & method | Frequency | Responsible |
| --- | --- | --- | --- | --- |

### 9.2 Evaluation questions

- To what extent did the campaign succeed in elevating HIV prevention as a sustained political priority at global, regional, and country levels, as evidenced by senior-level commitments, policy decisions, and institutionalised accountability mechanisms?

- To what extent did the campaign contribute to increased and protected financing for HIV prevention, including progress toward allocating at least 20% of national HIV budgets to prevention and establishing multi-year financing commitments

- How effectively did the campaign support the adoption or reform of policies, guidelines, and regulatory frameworks that enable timely approval, integration, and scale-up of combination and innovative HIV prevention options?

- To what extent did the campaign strengthen community led accountability mechanisms and meaningfully engage affected populations, particularly key populations and young people, in influencing prevention priorities and monitoring delivery?

- To what extent can observed changes in prevention access, coverage, and early uptake signals during 2026–2028 be plausibly linked to the campaign’s advocacy, financing, and policy interventions, considering contextual factors and risks?

### 9.3 Early impact signals (2026–28)

Describe what early signs of impact will look like by the end of 2028 (e.g. policy wins, financing decisions, coverage increases).

By early 2028, early signs of impact will be visible across political, financing, policy, and service-delivery domains. At the political level, HIV prevention will feature consistently in senior level statements, national development and health strategies, and formal accountability mechanisms, with documented commitments from Heads of State, Ministers of Health and Finance, and regional bodies translating into routine policy review and reporting. Prevention will no longer be treated as a discretionary or residual programme area, but as a recognised pillar of national HIV responses. In financing terms, early impact will be reflected in approved national budgets and medium-term expenditure frameworks that show protected or increased allocations for HIV prevention, including progress toward allocating at least 20% of total HIV budgets to prevention in priority countries. Evidence of multi-year budget commitments, co-financing arrangements with global partners, and reduced volatility in prevention funding will signal greater sustainability and predictability. Policy and regulatory progress will be evident through updated national HIV prevention strategies, the integration of combination and innovative prevention options into national guidelines and essential service packages and streamlined regulatory pathways that shorten timelines for approval and scale-up. Concrete implementation guidance and procurement decisions will indicate readiness to move beyond pilots toward national roll-out. Finally, early service-delivery and coverage signals will include stabilised or increasing access to prevention services in priority populations and locations, initial increases in uptake of PrEP and other prevention options, expanded community-led delivery and monitoring platforms, and improved continuity of prevention services, particularly in settings previously affected by funding or policy disruptions.

## STEP 10: Assess your risks

### 10.1 Risk register (global & country)

| Risk description | Level (H/M/L) | Likelihood (H/M/L) | Mitigation/contingency | Owner |
| --- | --- | --- | --- | --- |
| Political leadership shifts deprioritise HIV prevention due to elections, security crises, or leadership turnover | High | High | • Secure formal, written commitments (cabinet decisions, communiqués, budget statements) rather than reliance on individual champions • Anchor prevention commitments within national development plans and MTEFs • Use regional peer accountability (AU, SADC, ASEAN) to sustain momentum beyond electoral cycles | UNAIDS Executive Office; Regional Directors |
| Domestic HIV prevention budgets are reduced or reallocated during fiscal tightening | High | High | • Promote budget protection mechanisms (multi-year commitments) • Frame prevention as cost avoidance for ART liabilities to Ministries of Finance • Public tracking of prevention budget shares through community scorecard | UNAIDS Global Prevention Team; Global Fund liaison |
| Legal and policy barriers (criminalisation, age-of-consent laws, restrictive regulations) block equitable access to prevention | High | Medium | • Target political-level commitments for legal and policy reform (not only technical advocacy) • Support strategic litigation and policy dialogue through civil society partners • Use global and regional human rights mechanisms to apply pressure | UNAIDS Human Rights Team; Civil Society Partners |

### 10.2 Country-specific risk notes (To be completed during adaptation)

| Country | Key risks (3–5 bullet points) | Red lines / non-negotiables |
| --- | --- | --- |

## STEP 11: Phasing or exit strategy (ending December 2027/early 2028)

### 11.1 Campaign phases

| Phase | Period | Focus | Key milestones |
| --- | --- | --- | --- |
| Phase 1 – Launch & positioning | March- September 2026 | Establish the campaign as a global political priority and reframe HIV prevention as a political, financing, and development issue (a technical one). | • Global campaign launch aligned with a high level political moment (e.g. UNGA 2026, AU Summit) • Public articulation of the campaign narrative and core messages (“prevention as a political choice”) • Identification and engagement of priority countries and regions • High-level briefings with Heads of State, Ministers of Health and Finance in priority countries • Initial mapping of prevention financing gaps and policy bottlenecks • Community and civil society mobilisation begins (campaign branding, digital platforms, accountability framing) |
| Phase 2 – Political & financing commitments | October 2026–December 2027 | Secure, formalise, and institutionalise political, policy, and financing commitments for HIV prevention at global, regional, and country levels. | • Senior-level political commitments secured (cabinet decisions, ministerial statements, national communiqués) • Prevention explicitly prioritised in national development plans, health strategies, and MTEFs in priority countries • Progress toward ≥20% of national HIV budgets allocated to prevention documented in approved budgets • Financing commitments reinforced through Global Fund, World Bank, and other partner processes (co-financing, grant negotiations) • Policy and regulatory reforms initiated or completed (integration of prevention options into national guidelines and essential service packages) • Community-led accountability mechanisms operational (scorecards, public reporting, advocacy platforms) • Prevention featured consistently in major political and media moments (UNGASS, AU, G20, regional forums) |
| Phase 3 – Consolidation & hand-over | January–December 2027 / Early 2028 | Lock in gains, institutionalise accountability, and transition leadership to national and regional mechanisms while securing sustainability beyond the campaign. | Political commitments translated into routine accountability mechanisms (annual reporting, parliamentary or cabinet review) • Multi-year prevention financing commitments and budget protections confirmed • National ownership strengthened through government-led coordination and monitoring structures • Prevention scale-up pathways for combination and innovative tools clearly articulated and costed • Community-led monitoring embedded in national HIV responses • Campaign lessons documented and disseminated globally and regionally |

### 11.2 Minimum conditions by December 2027

List the minimum conditions for a responsible exit/transition (e.g. mechanisms, policies, financing, structures).

HIV prevention is explicitly prioritised in national political agendas in priority countries, reflected in:

- Formal senior-level commitments (e.g. cabinet decisions, ministerial statements, national communiqués), and

- Prevention embedded in national development plans, health strategies, or equivalent medium-term policy frameworks.

- National HIV budgets in priority countries demonstrate protected and/or increased allocations for prevention, with credible progress toward allocating ≥20% of total HIV financing to prevention.

- Prevention financing is reflected in approved budgets and medium-term expenditure frameworks, not only in policy statements or draft plans.

- Community-led monitoring and accountability mechanisms (e.g. scorecards, public reporting platforms, advocacy coalitions) are operational and linked to national prevention priorities in priority countries.

### 11.3 Digital & knowledge legacy

Describe what happens to campaign brand, digital assets, materials, datasets, and how learning will be documented and shared.

The Global HIV Prevention Campaign (2026–2028) will leave a durable digital, knowledge, and institutional legacy that supports sustained political prioritisation, financing accountability, and prevention scale-up beyond the formal campaign period.

The campaign brand, core narrative, and key messages will be formally retired as a time-bound advocacy campaign, while core framing elements (e.g. “prevention as a political and financing choice”) are integrated into UNAIDS’ ongoing prevention advocacy and communications.

## STEP 12: Communicate your campaign to UNAIDS Senior Leadership for approval

### 12.1 Funding and implementation scenarios for leadership decision

Use the scenarios below to frame strategic choices, trade-offs, and asks Senior Leadership based on different levels of funding availability.

Scenario 1: Adequate Funding Availability (Transformative Implementation)

Assumes sufficient and sustained funding to implement all four pillars of the campaign at scale across priority countries and populations. Aggressive, parallel, and comprehensive rollout of all four pillars to achieve rapid, transformative impact.

Scenario 2: Medium Funding (Pragmatic, Phased Implementation)

Assumes moderate but constrained funding, requiring deliberate choices on sequencing, geography, and populations to maximise catalytic effect. Strategic sequencing and catalytic investment. Focus on proving impact in high-priority geographies and populations to build political and financial momentum for wider scale-up.

Scenario 3: Worst-Case / Constrained Funding (Defensive & Foundational Implementation)

Assumes severe funding constraints and/or cuts, requiring a focus on protecting essential gains and community and service-delivery infrastructure. Protect core community infrastructure and leverage moral advocacy. Focus on preventing backsliding, securing foundational policy wins, and maintaining a platform for future scale-up when resources become available.

Summarise what will be included in the approval package (e.g. summary note, slide deck, risk summary, country overview).

### 12.2 Key messages and asks to Senior Leadership

Summarise the key decisions and support required from Senior Leadership.

| Ask #1 (decision/endorsement needed) |  |
| --- | --- |
| Ask #2 (resources/staffing) |  |
| Ask #3 (political backing/convening power) |  |
| Other key messages/considerations |  |

### 12.3 Engagement plan with leadership

| Senior leader/body | Purpose of engagement | Format (briefing, slide deck, meeting, etc.) | Timing | Lead person |
| --- | --- | --- | --- | --- |